## Installation Schedule
Phase | Duration (Days) | Start Date | End Date | Key Activities | Responsible Team | Milestones
Phase 1: Foundation & Base | 7 | Day 1 | Day 7 | Seafloor prep, base deployment, utility installation | Installation Team | Structural verification
Phase 2: Subsystem Integration | 7 | Day 8 | Day 14 | Life support, power, medical, COADA, XWP installation | Installation Team | Subsystem certification
Phase 3: System Testing | 7 | Day 15 | Day 21 | Integrated testing, mode verification, safety procedures | Testing Team | All systems certified
Phase 4: Crew Deployment | 7 | Day 22 | Day 28 | Crew deployment, handover, initial operations | Operations Team | Full operational status

## Personnel Requirements
Role | Quantity | Qualifications | Training Hours | Certification | Experience Required
Installation Manager | 1 | Project management, deep-sea ops | 40 | PMP, IMCA | 10+ years
Subsystem Engineers | 6 | Subsystem-specific expertise | 40 | Subsystem certification | 5+ years
Safety Officer | 2 | Safety management, emergency response | 40 | IMCA Safety | 8+ years
Operations Manager | 1 | System operations, crew management | 60 | Operations certification | 10+ years
Operations Technicians | 4 | System operation, troubleshooting | 60 | Operations certification | 5+ years
Medical Officer | 1 | Emergency medicine, dive medicine | 60 | Medical certification | 8+ years
Dive Master | 2 | Deep-sea diving, saturation diving | 80 | Advanced dive certification | 10+ years
Divers | 6 | Deep-sea diving operations | 80 | Deep-sea dive certification | 5+ years
Support Personnel | 4 | General maintenance, logistics | 20 | Safety certification | 2+ years

## Maintenance Schedule
Maintenance Type | Frequency | Duration (Hours) | Systems Affected | Required Parts | Responsible Personnel
Daily System Check | Daily | 2 | All systems | None (inspection only) | Operations Technician
Weekly Inspection | Weekly | 8 | All systems | Filters, seals, consumables | Maintenance Team
Monthly Overhaul | Monthly | 16 | Major systems | Replacement components | Senior Technician
Quarterly Certification | Quarterly | 24 | All systems | Calibration equipment | Certification Team
Battery Maintenance | Weekly | 4 | Power systems | Electrolyte, terminals | Power Technician
Gas System Check | Weekly | 3 | Life support | Gas samples, regulators | Life Support Tech
Water Treatment | Daily | 2 | Water systems | Treatment chemicals | Operations Technician
Communication Test | Daily | 1 | COADA system | None (testing only) | Communications Tech

## Performance Metrics
KPI | Target Value | Measurement Unit | Review Frequency | Acceptable Range | Action if Out of Range
System Uptime | 99.5% | Percentage | Daily | 99.0% - 100% | Investigate and repair
Power Efficiency | 95% | Percentage | Daily | 90% - 100% | System diagnostics
Gas Purity | 98% | Percentage | Daily | 97% - 100% | Gas replacement
Water Quality | 99% | Compliance % | Daily | 98% - 100% | Treatment adjustment
Communication Uptime | 99.9% | Percentage | Continuous | 99.5% - 100% | Switch to backup channel
Battery Capacity | 95% | Percentage | Weekly | 90% - 100% | Battery replacement
Pressure Stability | ±0.5 atm | Atmospheres | Continuous | ±1.0 atm | Pressure adjustment
Personnel Safety | Zero incidents | Count | Daily | Zero | Immediate investigation

## Emergency Procedures
Emergency Type | Initial Response | Escalation | Evacuation Required | Support Vessel Alert | Recovery Time
Medical Emergency | Medical officer assessment | Immediate treatment | If critical condition | Yes - immediate | 2-4 hours
System Failure | Activate backup system | Isolate failed system | If safety compromised | Yes - if critical | 4-8 hours
Pressure Loss | Activate pressure relief | Compartment isolation | Yes - immediate | Yes - immediate | 1-2 hours
Fire Emergency | Fire suppression activation | Area evacuation | Yes - immediate | Yes - immediate | Immediate
Communication Loss | Activate backup comms | Visual signal procedures | If prolonged loss | Yes - if loss >1 hour | 1-4 hours
Power Loss | Emergency backup activation | Load shedding procedures | If life support affected | Yes - if critical | 2-6 hours
Gas Contamination | Emergency breathing system | Activate backup gas supply | If severe contamination | Yes - if critical | 2-4 hours
Structural Damage | Compartment isolation | Damage assessment | Yes - if critical | Yes - immediate | 4-12 hours

## Supply Requirements
Supply Item | Unit | Daily Consumption | Weekly Requirement | Monthly Requirement | Storage Capacity
Oxygen | m3 | 2.5 | 17.5 | 75 | 150
Nitrogen | m3 | 1.2 | 8.4 | 36 | 100
Drinking Water | Liters | 240 | 1680 | 7200 | 2000
Food Supplies | kg | 15 | 105 | 450 | 500
Medical Supplies | kg | 0.5 | 3.5 | 15 | 50
Replacement Parts | Count | As needed | Variable | Variable | 500
Batteries | Units | 0.2 | 1.4 | 6 | 20
Treatment Chemicals | Liters | 5 | 35 | 150 | 300

## Training Curriculum
Training Module | Duration (Hours) | Target Audience | Prerequisites | Certification Required | Renewal Frequency
System Architecture & Design | 8 | All personnel | None | Yes | Annually
Installation Procedures | 16 | Installation team | System Architecture | Yes | As needed
System Operation & Control | 12 | Operations team | System Architecture | Yes | Annually
Emergency Procedures | 8 | All personnel | None | Yes | Quarterly
Deep-Sea Diving Operations | 24 | Dive team | Basic diving cert | Yes | Annually
Saturation Diving | 32 | Advanced dive team | Deep-sea diving cert | Yes | Annually
Medical Response & First Aid | 16 | Medical personnel | Medical background | Yes | Annually
Equipment Maintenance | 12 | Maintenance team | System Architecture | Yes | Annually
Safety & Environmental | 8 | All personnel | None | Yes | Annually